DOOFORM

Production Launch Plan

แผนการส่งมอบงานและเปิดใช้งานจริง

Target Launch: Mid-April 2026 (เมษายน 2569)

Document Version: 1.0

Last Updated: February 2026

# 1. Executive Summary

This plan outlines the 8-week sprint to take Dooform from its current MVP state (85% production-ready) to full production launch by mid-April 2026. The plan is organized into 4 phases covering technical hardening, internal testing, sales page delivery, and public launch.

| Launch Date | Current Readiness | Team | Phases |
| --- | --- | --- | --- |
| Mid-April 2026 | 85% Ready | Doc Team + Dev Team | 4 Phases / 8 Weeks |

# 2. Phase Overview

| Phase | Duration | Focus | Goal | Key Milestone |
| --- | --- | --- | --- | --- |
| Phase 1 | Feb 19 - Mar 5 | Build & Integrate | Feature Complete | Sales page design + 100 docs loaded |
| Phase 2 | Mar 5 - Mar 12 | Internal Testing | Stability | Internal users + feedback cycle |
| Phase 3 | Mar 12 - Mar 26 | Harden & Polish | Production Grade | Load test + accessibility pass |
| Phase 4 | Mar 26 - Apr 15 | Launch Prep | Go Live | Final QA + production deploy |

# 3. Detailed Sprint Plan

## Phase 1: Build & Integrate (Feb 19 - Mar 5)

Sprint focus: Complete sales page design, import production documents, and establish testing framework.

### Sprint 1 — Week of Feb 19

| Track | Task | Owner | Status | Priority |
| --- | --- | --- | --- | --- |
| DEV | Deliver Sales Page Design File | Dev Team | ☐ To Do | P0 - Critical |
| DEV | Refactor main app UI (SmartInput 44KB) | Dev Team | ☐ To Do | P1 - High |
| DEV | Prepare feedback collection sheet | Dev Team | ☐ To Do | P1 - High |
| DEV | Add API documentation (Swagger UI) | Dev Team | ☐ To Do | P1 - High |
| DEV | Implement circuit breakers (Typhoon AI, Gotenberg) | Dev Team | ☐ To Do | P0 - Critical |

### Sprint 2 — Week of Feb 26

| Track | Task | Owner | Status | Priority |
| --- | --- | --- | --- | --- |
| DOC | Deliver 100 corrected documents | Doc Team | ☐ To Do | P0 - Critical |
| DEV | Import documents into system | Dev Team | ☐ To Do | P0 - Critical |
| DEV | Write end-to-end tests for core flows | Dev Team | ☐ To Do | P1 - High |
| DEV | Implement per-user rate limiting | Dev Team | ☐ To Do | P1 - High |

## Phase 2: Internal Testing (Mar 5 - Mar 12)

Sprint focus: Deploy to internal users at Knight Visa and Visa To Go. Collect feedback and iterate.

### Sprint 3 — Week of Mar 5

| Track | Task | Owner | Status | Priority |
| --- | --- | --- | --- | --- |
| DOC | Open app to Knight Visa & Visa To Go users | Doc Team | ☐ To Do | P0 - Critical |
| DOC | Collect user feedback (1-week cycle) | Doc Team | ☐ To Do | P0 - Critical |
| DOC | Prepare additional documents for import | Doc Team | ☐ To Do | P1 - High |
| DEV | Build Sales Page from design file | Dev Team | ☐ To Do | P0 - Critical |
| DEV | Plan Information Architecture for Sales Page | Dev Team | ☐ To Do | P1 - High |
| DEV | Set up monitoring & alerting (Grafana/Datadog) | Dev Team | ☐ To Do | P1 - High |

## Phase 3: Harden & Polish (Mar 12 - Mar 26)

Sprint focus: Apply feedback, performance testing, partner outreach, and content preparation.

### Sprint 4 — Week of Mar 12

| Track | Task | Owner | Status | Priority |
| --- | --- | --- | --- | --- |
| DOC | Verify document accuracy in app | Doc Team | ☐ To Do | P0 - Critical |
| DOC | Intern: Create sales page content/copy | Intern | ☐ To Do | P1 - High |
| DEV | Contact DEPA partnership for product | Dev Team | ☐ To Do | P1 - High |
| DEV | Apply feedback from internal testing | Dev Team | ☐ To Do | P0 - Critical |
| DEV | Load testing (concurrent users, API throughput) | Dev Team | ☐ To Do | P0 - Critical |
| DEV | Accessibility testing (WCAG compliance) | Dev Team | ☐ To Do | P1 - High |

### Sprint 5 — Week of Mar 26

| Track | Task | Owner | Status | Priority |
| --- | --- | --- | --- | --- |
| DEV | Finalize App + Sales Page (code freeze) | Dev Team | ☐ To Do | P0 - Critical |
| DEV | Security audit (penetration testing basics) | Dev Team | ☐ To Do | P0 - Critical |
| DEV | Set up production infrastructure (DNS, SSL, CDN) | Dev Team | ☐ To Do | P0 - Critical |
| DEV | Backup & disaster recovery procedures | Dev Team | ☐ To Do | P1 - High |

## Phase 4: Launch Prep & Go Live (Apr 2 - Apr 15)

Sprint focus: Final product handoff, staging deployment, production cutover, and launch communications.

### Sprint 6 — Week of Apr 2

| Track | Task | Owner | Status | Priority |
| --- | --- | --- | --- | --- |
| DOC | Product handoff preparation (round 1) | Doc Team | ☐ To Do | P0 - Critical |
| DEV | Deploy to staging environment | Dev Team | ☐ To Do | P0 - Critical |
| DEV | Full regression testing on staging | Dev Team | ☐ To Do | P0 - Critical |
| DEV | Prepare rollback plan & runbook | Dev Team | ☐ To Do | P0 - Critical |

### Sprint 7 — Week of Apr 9 (LAUNCH WEEK)

| Track | Task | Owner | Status | Priority |
| --- | --- | --- | --- | --- |
| DOC | Product handoff preparation (round 2) | Doc Team | ☐ To Do | P0 - Critical |
| ALL | GO / NO-GO decision meeting | All Teams | ☐ To Do | P0 - Critical |
| DEV | Production deployment (target: Apr 15) | Dev Team | ☐ To Do | P0 - Critical |
| DEV | Post-deploy smoke testing & monitoring | Dev Team | ☐ To Do | P0 - Critical |
| ALL | Launch announcement (LINE, social, partners) | All Teams | ☐ To Do | P1 - High |

# 4. Production Launch Checklist

All items must be checked before GO decision on launch week.

### Technical Readiness

- Circuit breakers implemented on all external services (Typhoon AI, Gotenberg, GCS)

- Per-user rate limiting active

- API documentation (Swagger) published

- Load testing passed (target: 100+ concurrent users)

- Accessibility testing passed (WCAG 2.1 Level A minimum)

- Security audit completed (no critical/high vulnerabilities)

- Monitoring & alerting configured (uptime, error rates, latency)

- SSL certificates valid and auto-renewing

- Database backup & restore tested

- Rollback procedure documented and tested

### Content & Business Readiness

- 100+ document templates loaded and verified

- Sales page live with all sections (Hero, Features, Pricing, FAQ)

- Pricing tiers configured in payment system

- Terms of Service and Privacy Policy published (Thai + English)

- Customer support channel set up (LINE OA or email)

- Onboarding flow tested end-to-end

- DEPA partnership status confirmed

### Launch Day Operations

- Production environment deployed and smoke-tested

- DNS cutover completed

- War room / on-call schedule set for launch day

- Launch announcement prepared (LINE, social media)

- Post-launch monitoring dashboard visible to team

# 5. Risk Register

| Risk | Impact | Likelihood | Mitigation |
| --- | --- | --- | --- |
| Document team delays (100 docs) | High | Medium | Start with 50 highest-priority templates; add rest post-launch |
| OCR accuracy issues from feedback | Medium | Medium | Add manual override option; iterate OCR model post-launch |
| Load test failures | High | Low | Scale horizontally; optimize DB queries; add caching layer |
| Sales page not ready by launch | Medium | Medium | Launch app first with simple landing; full page follows |
| DEPA partnership delays | Low | High | Not a launch blocker; continue direct B2B sales |
| Songkran holiday impact (Apr 13-15) | Medium | High | Target launch before Apr 13 or after Apr 16 to avoid holiday |

# 6. Post-Launch Success Metrics (First 30 Days)

| Metric | Target | Measurement |
| --- | --- | --- |
| Uptime | 99.5%+ | Monitoring dashboard |
| Registered Users | 50+ | User database |
| Documents Generated | 200+ | Analytics |
| OCR Scans Used | 100+ | Analytics |
| Critical Bugs Reported | < 5 | Issue tracker |
| Paying Customers | 5-10 | Payment system |

# 7. Key Dates Summary

Important: Songkran holiday falls on April 13-15. Plan production deployment either before April 11 or after April 16.

| Date | Milestone | Type |
| --- | --- | --- |
| Feb 19 | Sprint 1 kickoff | Sprint Start |
| Mar 5 | Internal testing begins (Knight Visa / Visa To Go) | Milestone |
| Mar 12 | DEPA outreach + feedback implementation | Milestone |
| Mar 26 | Code freeze (App + Sales Page final) | Critical Gate |
| Apr 2 | Staging deployment + regression testing | Milestone |
| Apr 9-11 | GO/NO-GO decision + production deploy | Critical Gate |
| Apr 13-15 | Songkran Holiday (no deploy) | Holiday Block |
| Apr 16 | Post-holiday launch (fallback date) | Backup Launch |